## Sheet1
Epic | Requirement | Development | Estimate | Priority | Description | Status
Green = done but not tested, yellow means in progress
Buy
Be 1st consistently
|  | If necessary we can increase aws server size | 2 hr |  |  | with the new Scale Node we are paying for and the the auto Sell features we'll make additional progress. Then we can iterate on the progress. Currently we are using an AWS t2.2xlarge. It has 8 cores and some memory but it's still just a starter box. So we will start to see exponential progress. A decent goal is at least 4 64 core boxes with 255gb of memory. | Switched Cards
|  | if necessary we can move the buy from backend to frontend | 4 days
Auto approve after the buy
|  | Call current Approve method after Buy completes | 1 hr | 1 | We will auto approve each buy directly after the buy and before the sell | I added an "Allowance" check to keep us from double buying. The "Buy" method waits for the "addLiquidity" Tx, then the allowance checks waits for the buy action to complete, then the approve method is called if necessary.
Auto Buy
|  | queue match | 3 hr | 1 | make sure any keywords we have indentifed as "strong buy" shows up in this queue where we can auto buy any new liq add | Adding a specific contract to monitor is done on the Front End. But the back end has been refactored for auto-sell. and also logging every liquidy add, our current contract analysis and remove liquidity event.
|  | Configurable Buy amount | 2 hr | 1 | be able to adjust how much we want to auto buy for any new liq add
|  | Enter contract address moment it adds liquidity | 3 hrs | 1b | enter in any contract address we want to listen for, when they add liq buy
Sell
Sell amount specified
|  | Sell using uniswap sdk | 2 hr | 1 |  | Production is currently using the uniswap sdk. We have 2 additional web3 sell methods. One using the method calls that metamask uses. The second allow for slippage on both the amount of units to sell as well as ETH expected.
|  | Sell using web3 api | 4 hr
front rug (auto sell)
|  | Sell when we see Remove Liqudiity | 8 hr | 1b | Will sell before the dev can remove liquidity | The my first design of Auto-Rug feature was using other components and services. Which made the code sloppy, so I moved it into its own service.
|  | Sell when we see a particular wallet selling | 3 hr |  | We can enter a wallet and sell before that wallet can sell which would allow us to get out before they mint and dump | Selling when when a know wallet sells will be integrated with the contract/liquidity feature The same for selling when we see a particular method sell.
|  | Sell when a Contract function is called | 4 hr |  | If they call a function that will not let us sell like setmaxslippage we can sell before this function is executed
Sell when achieve x% of profit gain
|  | Update and integrate Limit Order Service | 8 hr | 1 | Be able to buy/sell with limit orders any contract address, automatically add any contract purchased from the new liq add memepool to our limit order service
Sell % of tokens
|  | Based of % increase | 1 hr | 1 | Ladder Sell and MoonBag: we will be able to sell x% of the tokens based upon n% of growth, being able to create ladders of these sells, along with selling the whole position but keeping x% for a moonbag
Filters
\
Categorize Contracts into different queue's
|  | Apply Rules to identified set of Contract functions | 1 hr | 1 | This gives us an interface where we can add lines of code or functions, group them and lable them by a specific keyword, then based upon that keyword have new liq adds sent to the proper queues
|  | Identify most commonly used methods and review for addition to rules | 2 hr |  | This is currently on going in the product bot channel on discord
|  | Save Contract methods of all Buy/Sell tx's to define categories | 8 hr |  | With logging we will be able to indentify any new functions being used and apply rules as pointed out above
|  | Score contracts by P&L | 24 hr |  | We will be able to keep track of our P&L by keyword and queue type so we can identify what contract types yeild the most ROI, so that we many eventually tweak the gas/slippage and spend amount dynamically
Queues
| Strong Buy |  |  | 1
|  | Create strong buy queue |  |  | With a strong buy queue, the bot will automatically buy any contract with our strong buy keywords | use exisiting keywords that we have labled strong buy and have them show up in this queue
Buy
|  | Create buy queue | 3 hr | 1 | With a buy queue, we will know we can safely buy these contracts even though its most likely a rug | use exisiting keywords that we have labled buy and have them show up in this queue
NFT drop queue
|  | Identify 721 Contracts | N/A |  | We will be able to buy NFTs when the drop happens, any new erc-721 drop will show up in this queue
|  | Update UI with new window | N/A
Non-Categorized queue
|  | Create non-categorized | 1hr | 1 | anything not in the other queues or the blacklist will show up here giving us a chance to categorize them
Blacklist
|  | Create blacklist queue |  | 1c | this will be any bad contracts we should never have in any queue
Allow Categorization through UI
|  | Save Contract function set and queue | 3 hrs |  | This will enable us to quickly add any contract type in the queue to a different queue
|  | Add set to queue to filter | 1 hr |  | Larry don't know what this means
|  | Group functions, save keyword name, add to queue | 16hr |  | Larry how is this different than C31?
UI
Add keywords after the buy signal
|  | Add new div for clean look | 1 hr | 1 | This shows us the function keywords after the word buy, strong buy, risky etc.. | This is live on prod
See all tx's on Contract
|  | Add new window | 10 hr |  | We can see any new txts for a particular contract, this will enable us to see a big buy and sell after or front run someone with a buy simply by clicking on that transaction. We can also see if the dev is calling a specific function | I need to restructure the DB and migrate
Buy Click confirmed
|  | Add Javascript confirmation | 1 hr | 1 | This just confirms that the listener has started to buy a new liq add | This is live on prod
Kill Transaction
|  | If Eth Amount == 0 send previous nonce tx with 0 Eth | 5 hr | 1c | This will enable us to manaully kill any txt buy sending 0 eth with the same nonce
Show # of holders and top 10 holders plus how much they own
|  | Pull from Contract, or Check if etherscan has this api | N/A |  | On each contract we will be able to see the total amount of holders, who owns what percentage as as pie graph. This will help us decide a level of risk or if there was a presale
Hide Button that will hide any transaction in the queue
|  | Add Javascript to Contract div | 2 hr |  | this gets txt's out of the way in the queue, I have bought a bad contract before thinking it was the right one and it was a scam contract that came out right before the legit launch
| Elon Musk tweets in a window, when he tweets stuff goes nuts | N/A |  |  | We could have a queue just for new elon tweets that scans his text and tries to match up any of that text with the contract name to auto buy, assuming the contract has strong buy functions