## SmartPSA
TaskId |  | Task Decription | Estimated Hours | Expended Hours | Difference | Status | Last Update | Notes | Completed
| Algorithmic Development | [7 empty] | In Progress
SST-01AD | Translate Base Matlab functions to respsective R Equivalients |  |  |  | 0 | Outstanding | 2018-08-14 |  | Outstanding
SST-02AD | Integrate R functions for rolling horizon calculation |  |  |  | 0 | Outstanding | 2018-08-14
SST-03AD | Integrate R functions forParallelize computation |  |  |  | 0 | Outstanding | 2018-08-14
Backend Databases
| HBase:Storing time-series data |  |  |  | 0 | Outstanding | 2018-08-14
SST-01DB |  | HBase: Prep and testing (including Hadoop) | 10 | 6 | 4 | In Progress | 2018-08-14
OpenTSDB: Storing time-series data
SST-02DB |  | OpenTSDB: Base install | 24 | 24 | 0 | Completed | 2018-08-14
SST-03DB |  | OpenTSDB: Define schema | 24 | 24 | 0 | Completed | 2018-08-14
|  | Documentation of the schema opentsdb | 16 | 1 | 15 | In Progress | 2018-08-14
SST-04DB |  | OpenTSDB: Data infusion and testing | 24 | 24 | 0 | In Progress | 2018-08-14
MongoDB
SST-05DB |  | Run under admin user | 4 | 2 | 2 | Completed | 2018-08-14
MySQL
SST-06DB |  | Run under admin user | 4 | 2 | 2 | Completed | 2018-08-14
Data Acquisition API’s and Services
Batch data download
SST-01API |  | Add OpenTSDB access and download | 16 | 32 | -16 | Outstanding | 2018-08-14
SST-02API |  | Run under admin user | 4 | 0 | 4 | Outstanding | 2018-08-14
SST-03API |  | Format dates and times | 4 | 0 | 4 | Outstanding | 2018-08-14
Streaming data acquisition
SST-04API |  | Update Import and formatter for OpenTSDB download | 24 | 8 | 0 | In Progress | 2018-08-14
SST-05API |  | Create DB API in NodeJS with parameters for OpenTSDB and MySQL | 24 | 0 | 0 | Outstanding | 2018-08-14
SST-06API |  | Format dates and times | 4 | 0 | 0 | Outstanding | 2018-08-14
Frontend Application
SST-01FE | Optimize trend viewer of high frequency data |  | 40 | 0 | 40 | Outstanding | 2018-08-14
SST-02FE | Trend visualization for OpenTSDB |  | 8 | 0 | 8 | Outstanding | 2018-08-14
SST-03FE | Install MongoDb viewer |  | 2 | 0 | 2 | In Progress | 2018-08-14
SST-04FE | Install MySql Workbench |  | 2 | 1 | 1 | Completed | 2018-08-14
Feature Performance Reporting and Evaluation
SST-01BM | Database read time for OpenTSDB |  | 12 | 0 | 12 | Outstanding | 2018-08-14
SST-02BM | Database write time for OpenTSDB |  | 12 | 0 | 12 | Outstanding | 2018-08-14
SST-03BM | Centralize benchmarking into generic method |  | 0 | 0 | 0 | Outstanding | 2018-08-14
6.45

## Weekly
Date | Work Week | Algorithmic Development | Backend Databases | Data Acquisition API’s and Services | Frontend Application | Feature Performance Reporting and Evaluation | Total Weekly Hrs
2018-04-25 | Week1 hrs |  | 30 | 10 |  |  | 40
2018-05-02 | Week2 hrs |  | 30 | 10 |  |  | 40
2018-05-09 | Week3 hrs |  | 15 | 15 |  |  | 30
2018-05-16 | Week4 hrs |  | 15 | 15 |  |  | 30
2018-05-23 | Week 5 hrs | [5 empty] | 0
2018-05-30 | Week 6 hrs | [5 empty] | 0
2018-06-05 | Week 7 hrs | [5 empty] | 0